## Start Here
Renovation Timeline Template
Free from rumaruma.com.my. Fill in the yellow cells; everything else updates by itself.
1. Your details
Property type | Condo / Apartment | Changes the default durations. Choose Landed house for terrace, semi-D or bungalow.
Planning start date | 2026-11-02 | The day you start meeting designers or contractors.
Target move-in date | 2027-04-30 | The date you'd like to move in.
Does your contractor work on Saturdays? | Yes | Most do. Some condos ban Saturday work; check your management's house rules.
Contingency buffer (% of site work days) | 20% | Extra time for delays. 20–30% is realistic.
Contract sum (RM) | 80000 | Used on the Payments tab. Leave as is if you don't have a quote yet.
2. Your results (calculated)
Site works start (hacking begins) | 2026-12-01
Handover (snagging done) | 2027-03-19
Ready to move in (including buffer) | 2027-04-06
Days to spare before your target move-in | 24
Status | On track | If you're behind, start planning earlier, raise the Saturday option with your contractor, or reduce the scope.
Site works, start to move-in (weeks) | 18.1
3. How to use this template
1. Fill in the yellow cells above. Dates update on every tab.
2. Timeline tab: once your contractor gives you their schedule, type their days into the yellow "Your estimate" column.
3. Holidays tab: add your state's holidays and your contractor's actual festive break dates. These days are skipped.
4. Gantt tab: a week-by-week chart of the whole job. Grey numbers show public holidays and festive break days in that week.
5. Orders & Approvals tab: shows the last day to decide or order each item so it doesn't hold up the work.
6. Payments tab: links each progress payment to a finished stage of work.
7. Site Visits tab: log what you checked, what needs fixing and by when.
4. Key
Yellow cell | Fill in or change
White cell | Calculated; don't type over it
Default durations are rumaruma estimates for a typical full renovation, counted in working days. Your contractor's schedule should replace them. Holiday dates for 2027 come from published lists; Islamic holidays depend on moon sighting, so check the official list. This template is a planning aid, not professional advice.
More renovation guides: rumaruma.com.my/how-long-does-a-full-home-renovation-take-in-malaysia/

## Timeline
Timeline
Dates skip Sundays, public holidays and festive breaks (and Saturdays if you chose No). Edit only the yellow columns.
# | Phase | What happens | Typical days: condo | Typical days: landed | Your estimate (work days) | Work days used | Start | End | Approx. weeks | Overlap with previous phase (work days) | Who | Status | Notes
1 | Design, quotations & contract | Brief your ID or contractor, compare at least three quotations, finalise drawings and sign the contract. | 15 | 20 |  | 15 | 2026-11-02 | 2026-11-18 | 2.4 | — | You + ID / contractor | Not started
2 | Management / council approvals | Condo: submit the renovation application, pay the deposit to the JMB/MC and get worker passes. Landed: check whether your PBT (e.g. DBKL, MBPJ) needs a permit, and tell your neighbours. | 10 | 10 |  | 10 | 2026-11-19 | 2026-11-30 | 1.7 |  | Contractor + you | Not started
3 | Hacking & debris removal | Remove old tiles, walls, cabinets and ceilings. Debris is cleared from the site. | 5 | 8 |  | 5 | 2026-12-01 | 2026-12-05 | 0.7 |  | Contractor | Not started
4 | Plumbing, electrical & aircond piping | Concealed pipes and wiring, new power points, aircond piping. Take photos before walls and ceilings are closed. | 12 | 18 |  | 12 | 2026-12-07 | 2026-12-19 | 1.9 |  | Contractor | Not started
5 | Waterproofing & ponding test | Waterproof bathrooms, yard and balcony, then a ponding test of at least 24–48 hours before tiling. | 4 | 5 |  | 4 | 2026-12-21 | 2026-12-24 | 0.6 |  | Contractor | Not started
6 | Ceiling & partitions | Plaster ceiling, cove lighting boxes and drywall partitions. The carpenter measures the site after this. | 10 | 15 |  | 10 | 2026-12-26 | 2027-01-07 | 1.9 |  | Contractor | Not started
7 | Tiling & flooring | Floor and wall tiles, vinyl or timber flooring. | 12 | 18 |  | 12 | 2027-01-08 | 2027-01-21 | 2 |  | Contractor | Not started
8 | Built-in carpentry installation | Kitchen cabinets, wardrobes, TV console. Factory fabrication happens before this; see the Orders & Approvals tab. | 8 | 12 |  | 8 | 2027-01-22 | 2027-01-30 | 1.3 |  | Carpenter | Not started
9 | Painting | Skim coat, sealer and two finishing coats. | 7 | 12 |  | 7 | 2027-02-01 | 2027-02-19 | 2.7 |  | Painter | Not started
10 | Fit-out: countertop, sanitary & lights | Countertop, sinks, taps, WC, water heater, light fittings, hood and hob. | 8 | 10 |  | 8 | 2027-02-20 | 2027-03-01 | 1.4 |  | Contractor | Not started
11 | Final cleaning | Post-renovation cleaning before the snag walk-through. | 2 | 3 |  | 2 | 2027-03-02 | 2027-03-03 | 0.3 |  | Cleaning crew | Not started
12 | Snagging & defect fixing | Walk through with your snag list, the contractor fixes defects, then hands over the keys. | 8 | 10 |  | 8 | 2027-03-04 | 2027-03-19 | 2.3 |  | You + contractor | Not started
13 | Contingency buffer | Spare time for delays: late materials, rain, defects found during hacking, changes you make mid-way. Percentage set on the Start Here tab. |  |  |  | 15 | 2027-03-20 | 2027-04-06 | 2.6 |  | —
| Ready to move in | [6 empty] | 2027-04-06
Notes
Phases run one after another. If your contractor runs two phases side by side, enter the overlapping work days in the yellow Overlap column.
Typical days are working days, not calendar days. Six working days is about one week if your contractor works Saturdays.
Durations are rumaruma estimates for a full renovation of an existing home; a partial renovation will be shorter.
Formulas:
Start = WORKDAY.INTL([End, row above],1-N([Overlap with previous phase (work days)]),IF(SatWork="Yes","0000001","0000011"),HolidayDates)
Start = IF([Work days used]=0,[End, row above],WORKDAY.INTL([End, row above],1,IF(SatWork="Yes","0000001","0000011"),HolidayDates))
End = WORKDAY.INTL([Start],MAX([Work days used],1)-1,IF(SatWork="Yes","0000001","0000011"),HolidayDates)
End = IF([Work days used]=0,[End, row above],WORKDAY.INTL([Start],MAX([Work days used],1)-1,IF(SatWork="Yes","0000001","0000011"),HolidayDates))

## Gantt
Gantt chart
One column per week (Monday start). Shaded bars show when each phase runs. The grey row counts holiday and festive break days in each week.
# | Phase | Start | End | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45
 | time axis 2026-11-02 to 2027-09-06
| Holiday / festive break days |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 5 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0
1 | Design, quotations & contract | 2026-11-02 | 2026-11-18 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Management / council approvals | 2026-11-19 | 2026-11-30 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Hacking & debris removal | 2026-12-01 | 2026-12-05 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Plumbing, electrical & aircond piping | 2026-12-07 | 2026-12-19 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Waterproofing & ponding test | 2026-12-21 | 2026-12-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Ceiling & partitions | 2026-12-26 | 2027-01-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Tiling & flooring | 2027-01-08 | 2027-01-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Built-in carpentry installation | 2027-01-22 | 2027-01-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Painting | 2027-02-01 | 2027-02-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Fit-out: countertop, sanitary & lights | 2027-02-20 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Final cleaning | 2027-03-02 | 2027-03-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Snagging & defect fixing | 2027-03-04 | 2027-03-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Contingency buffer | 2027-03-20 | 2027-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dark week number = this week. Light bar = contingency buffer.

## Orders & Approvals
Orders & Approvals
Decide or order each item by the date in column E so it doesn't hold up the work. Change the phase or lead time to suit your project.
Item | Needed before this phase starts | Phase starts | Lead time (work days) | Decide / order by | Days left | Status | Notes
Aircond units and piping positions | Plumbing, electrical & aircond piping | 2026-12-07 | 5 | 2026-12-01 | 47 | To do | Piping is hidden in the walls and ceiling during electrical and plumbing works.
Power point and lighting positions | Plumbing, electrical & aircond piping | 2026-12-07 | 5 | 2026-12-01 | 47 | To do | Walk through each room with your contractor and mark them on the floor plan.
Water heater type (instant or storage) | Plumbing, electrical & aircond piping | 2026-12-07 | 5 | 2026-12-01 | 47 | To do | A storage heater needs different pipes and power.
Kitchen appliances (hob, hood, oven, fridge size) | Plumbing, electrical & aircond piping | 2026-12-07 | 5 | 2026-12-01 | 47 | To do | Sizes decide cabinet cut-outs and power points.
Floor and wall tiles | Tiling & flooring | 2027-01-08 | 10 | 2026-12-26 | 72 | To do | Allow 15–20 days for imported or special-order tiles. Buy about 10% extra for cuts and future repairs.
Carpentry drawings approved, fabrication ordered | Built-in carpentry installation | 2027-01-22 | 20 | 2026-12-29 | 75 | To do | Factory fabrication usually takes 3–5 weeks after the carpenter measures the site.
Paint colours and finishes | Painting | 2027-02-01 | 5 | 2027-01-26 | 103 | To do | Test samples on your actual walls in daylight and at night.
Kitchen countertop | Fit-out: countertop, sanitary & lights | 2027-02-20 | 10 | 2027-01-28 | 105 | To do | The fabricator measures after the cabinets are installed; confirm their timing.
Sanitary ware and taps | Fit-out: countertop, sanitary & lights | 2027-02-20 | 10 | 2027-01-28 | 105 | To do | Check stock early; popular models can be out of stock for weeks.
Light fittings and fans | Fit-out: countertop, sanitary & lights | 2027-02-20 | 10 | 2027-01-28 | 105 | To do
Cleaning crew booked | Final cleaning | 2027-03-02 | 5 | 2027-02-24 | 132 | To do
Curtains and blinds | Snagging & defect fixing | 2027-03-04 | 10 | 2027-02-20 | 128 | To do | The installer measures after painting.
Loose furniture and mattresses | Snagging & defect fixing | 2027-03-04 | 15 | 2027-02-15 | 123 | To do | Arrange delivery for after handover.
Electricity, water and internet accounts | Snagging & defect fixing | 2027-03-04 | 10 | 2027-02-20 | 128 | To do | Transfer or open accounts so everything works on move-in day.
Red row = past the order date. Orange row = due within 14 days. Grey text = ordered or done.
Formulas:
Phase starts = IFERROR(INDEX(Timeline!$H5:H16,MATCH([Needed before this phase starts],Timeline!$B5:B16,0)),"")
Decide / order by = IF([Phase starts]="","",WORKDAY.INTL([Phase starts],-[Lead time (work days)],IF(SatWork="Yes","0000001","0000011"),HolidayDates))
Decide / order by = IF(OR([Phase starts]="",[Lead time (work days)]=""),"",WORKDAY.INTL([Phase starts],-[Lead time (work days)],IF(SatWork="Yes","0000001","0000011"),HolidayDates))
Days left = IF([Decide / order by]="","",[Decide / order by]-TODAY())

## Payments
Payments
Link each payment to finished work, never to a calendar date. This is an example schedule; agree yours in the contract.
Contract sum: | 80000
Payment stage | Due when this phase is done | Expected date | % of contract | Amount (RM) | Paid on | Notes
Deposit on signing | Design, quotations & contract | 2026-11-18 | 20% | 16000 |  | Many contracts ask for 10–30%. Pay to the company account, not a personal one, and get a receipt.
Progress 1: hacking and wiring done | Plumbing, electrical & aircond piping | 2026-12-19 | 25% | 20000 |  | Check the concealed wiring and pipes (and your photos) before paying.
Progress 2: tiling done | Tiling & flooring | 2027-01-21 | 25% | 20000 |  | Tap-test the tiles for hollow sounds before paying.
Progress 3: carpentry and painting done | Painting | 2027-02-19 | 20% | 16000
Final payment: defects fixed | Snagging & defect fixing | 2027-03-19 | 10% | 8000 |  | Keep this until your snag list is fully fixed.
Total |  |  | 100% | 80000 |  | Adds up to 100%
Paid so far |  |  |  | 0
Formulas:
Expected date = IFERROR(INDEX(Timeline!$I5:I16,MATCH([Due when this phase is done],Timeline!$B5:B16,0)),"")

## Site Visits
Site visit log
Note what you checked on each visit. Send the issues to your contractor in writing (WhatsApp is fine) and record the agreed fix date.
Date | Phase | What I checked | Issues found | Who fixes it | Fix by | Fixed? | Photos / notes
2026-12-14 | Plumbing, electrical & aircond piping | Pipe routes in master bathroom before walls are closed | Hot water pipe not insulated | Plumber (via contractor) | 2026-12-16 | No | Example row: replace with your own

## Holidays
Holidays and festive breaks
Work stops on these dates, so the Timeline skips them. Add your state's holidays and your contractor's actual festive break; delete what doesn't apply.
Islamic holiday dates depend on moon sighting; check the official list each year. Festive breaks are typical, not fixed: ask your contractor when their workers go home.
Date | Holiday or break | Type
2026-11-08 | Deepavali (not Sarawak) | Public holiday
2026-12-25 | Christmas Day | Public holiday
2027-01-01 | New Year's Day (not Johor, Kedah, Kelantan, Perlis, Terengganu) | Public holiday
2027-02-03 | Chinese New Year break: workers off (typical) | Festive break
2027-02-04 | Chinese New Year break: workers off (typical) | Festive break
2027-02-05 | Chinese New Year break: workers off (typical) | Festive break
2027-02-06 | Chinese New Year | Public holiday
2027-02-07 | Chinese New Year (day 2) | Public holiday
2027-02-08 | Chinese New Year (replacement day) | Public holiday
2027-02-09 | Chinese New Year break: workers off (typical) | Festive break
2027-02-10 | Chinese New Year break: workers off (typical) | Festive break
2027-02-11 | Chinese New Year break: workers off (typical) | Festive break
2027-02-12 | Chinese New Year break: workers off (typical) | Festive break
2027-02-13 | Chinese New Year break: workers off (typical) | Festive break
2027-02-14 | Chinese New Year break: workers off (typical) | Festive break
2027-03-08 | Hari Raya break: workers off (typical) | Festive break
2027-03-09 | Hari Raya break: workers off (typical) | Festive break
2027-03-10 | Hari Raya Aidilfitri (estimated) | Public holiday
2027-03-11 | Hari Raya Aidilfitri day 2 (estimated) | Public holiday
2027-03-12 | Hari Raya break: workers off (typical) | Festive break
2027-03-13 | Hari Raya break: workers off (typical) | Festive break
2027-03-14 | Hari Raya break: workers off (typical) | Festive break
2027-05-01 | Labour Day | Public holiday
2027-05-17 | Hari Raya Haji (estimated) | Public holiday
2027-05-20 | Wesak Day | Public holiday
2027-06-06 | Awal Muharram (estimated) | Public holiday
2027-06-07 | Yang di-Pertuan Agong's Birthday | Public holiday
2027-08-15 | Maulidur Rasul (estimated) | Public holiday
2027-08-31 | National Day | Public holiday
2027-09-16 | Malaysia Day | Public holiday
2027-10-28 | Deepavali (not Sarawak) | Public holiday
2027-12-25 | Christmas Day | Public holiday